## Sheet1
prototype | Store # | City |  | ST | Water test kit PO# & date sent out | date rec'd water test kits back | Ord#&Chick-fil-A PO# | PO# & date to installer | Ship Date | TDS | Hardness | Current Equipment | Up Taste | Status | Comments | Water Softener Needed | Existing Water Softener | NEW Water Test Needed | Recommendations
HARD WATER UNITS
| 14 | Lake Jackson |  | TX | 156261 10/27/03 | 2003-12-02 |  |  |  | 550 | 143 |  |  |  |  | NO | NO | NO
| 28 | West Miffliin |  | PA | 228242 10/3/05 | 2005-10-21 |  |  |  | 320 | 155 | [5 empty] | NO | DONE
| 33 | El Paso |  | TX | 156165 10/27/03 | 2003-11-05 |  |  |  | 550 | 146 |  |  |  | water softner on site but not working | water softner on site but not working | YES BUT NOT WORKING | NO
| 68 | Mount Hope |  | WV | 228236 10/3/05 | 2005-10-21 |  |  |  | 300 | 82 |  | NO |  |  |  |  | DONE
| 102 | Lexington |  | KY | 228279 10/3/05 | 2005-10-19 | 222696 M66616 | install handled on site | 2005-07-13 | 280 | 322 | BYPASS UNITS PKG B |  |  |  |  | NO | DONE
| 137 | Barboursville |  | WV | 228241 10/3/05 | 2005-10-25 |  |  |  | 340 | 167 |  |  | NEW |  |  |  | DONE
| 155 | San Antonio |  | TX | 156299 10/27/03 | 2003-11-11 |  |  |  | 300 | 280 |  |  |  |  | YES | NO | NO
| 162 | Lufkin |  | TX | 156271 10/27/03 | 2003-11-05 |  |  |  | 350 | 15 |  |  |  | water softner on site | water softner on site | YES | NO
| 166 | Abilene |  | TX | 144209 8/26/03 | 2003-10-31 |  |  |  | 700 | 209 |  |  |  |  | NO | NO | NO
| 167 | Laredo |  | TX | 156263 10/27/03 | 2003-11-11 | 205192 M53155 | install handled on site | 2005-01-10 | 400 | 227 | 2 - P | NO |  |  | NO | NO | NO
CIF Mall | 169 | Midland | 1 | TX | 156280 10/27/03 | 2003-11-07 |  |  |  | 1700 | 444 |  |  |  | water softner on site | water softner on site | YES | NO
| 181 | Houston |  | TX | 156180 10/27/03 | 2003-12-15 |  |  |  | 300 | 21 |  |  |  |  | NO | NO | NO
| 184 | San Antonio |  | TX | 156300 10/28/03 | 2003-11-13 |  |  |  | 260 | 280 |  |  |  |  | YES | NO | NO
CIF Mall | 193 | McAllen | 1 | TX | 156274 10/27/03 | 2003-11-15 |  |  |  | 800 | 254 |  |  |  |  | YES | NO | NO
CIF Mall | 208 | Enid | 1 | OK | 165982 2/4/04 | 2004-02-18 |  |  |  | 370 | 288 |  |  |  | requested by Greg Bishop | YES | NO | NO
| 217 | Sherman |  | TX | 156279 10/28/03 | 2003-11-07 |  |  |  | 430 | 122 |  |  |  | water softner on site | water softner on site | YES | NO
CIF Mall | 244 | Odessa | 1 | TX | 156285 10/28/03 | 2003-11-07 |  |  |  | 1600 | 448 |  |  |  | water softner on site | water softner on site | YES | NO
| 265 | Mary Esther |  | FL | 229715 11/7/05 | 2005-11-17 |  |  |  | 340 | 21 |  |  | NEW |  |  | NO | DONE
| 269 | Gautier |  | MS | 95008 4/4/02 | 2002-04-18 | 125310 56133 | 1054 3/26/03 | 2003-05-15 | 390 | 2 | 2 - P | UP |  |  | NO | NO | NO
| 287 | College Station |  | TX | 156151 10/23/03 | 2003-11-07 |  |  |  | 420 | 25 |  |  |  | water softner on site | water softner on site | YES | NO
| 288 | Brownsville |  | TX | 144227 8/26/03 | 2003-09-10 |  |  |  | 850 | 226 |  |  |  | water softner on site | water softner on site | YES | NO
CIF Mall | 289 | San Angelo | 1 | TX | 156297 10/27/03 | 2003-11-05 |  |  |  | 1500 | 430 |  |  |  |  | YES | NO | NO
CIF Mall | 290 | Lubbock | 1 | TX | 158793 12/12/03 | 2004-01-06 |  |  |  | 1100 | 294 |  |  |  |  | YES | NO | NO
| 315 | Mishawaka |  | IN | NA | 2005-09-12 | 227869 M75218 | install handled on site | 2005-09-26 | 380 | 216 | Coffee & Ice Pro, 20" prefilter | NO |  |  |  | NO | DONE
| 319 | Victoria |  | TX | 156347 10/28/03 | 2003-11-13 |  |  |  | 300 | 159 |  |  |  |  | NO | NO | NO
| 330 | Tampa |  | FL | 229684 10/26/05 | 2005-11-03 |  |  |  | 340 | 214 |  | No | NEW |  |  | NO | DONE
??? | 334 | Phoenix | 1 | AZ | 168221 3/23/04 | 2004-04-13 | 168220 M33015 | MS | 3/23/04 | 600 | 283 | 2 - P | UP |  |  | YES | NO | NO
| 336 | Amarillo |  | TX | 144213 8/26/03 |  |  |  |  | 900 | 233 |  |  |  | water softner on site | water softner on site | YES | NO
| 341 | Harlingen |  | TX | 156179 10/28/03 |  |  |  |  | 800 | 206 |  |  |  | water softner on site | water softner on site | YES | NO
| 350 | San Antonio |  | TX | 156303 10/27/03 |  |  |  |  | 350 | 242 |  |  |  |  | NO | NO | NO
| 357 | Vero Beach |  | FL | 230580 11/7/05 | 2005-11-16 |  |  |  | 370 | 110 |  |  | NEW |  |  |  | DONE
| 359 | San Antonio |  | TX | 156304 10/27/03 |  |  |  |  | 250 | 329 |  |  |  |  | YES | NO | NO
| 365 | Canton |  | OH | 228269 10/3/05 | 2005-10-14 |  |  |  | 500 | 172 | [6 empty] | DONE
| 395 | Fort Myers |  | FL | 229669 10/25/05 | 2005-11-08 |  |  |  | 400 | 57 |  |  | NEW |  |  |  | DONE
| 438 | Cincinnati |  | OH | 228267 10/3/05 | 2005-10-14 |  |  |  | 320 | 163 | [6 empty] | DONE
| 456 | Cincinnati |  | OH | 228266 10/3/05 | 2005-10-19 |  |  |  | 300 | 173 | [6 empty] | DONE
| 457 | Bryan |  | TX | 144228 8/26/03 | 2003-09-10 |  |  |  | 650 | 37 |  |  |  | water softner on site | water softner on site | YES | NO
| 492 | Spring |  | TX | 156342 10/27/03 | 2003-11-07 |  |  |  | 350 | 54 |  |  |  | water softner on site | water softner on site | YES | NO
| 561 | Youngstown |  | OH | 228251 10/3/05 | 2005-10-19 |  |  |  | 600 | 208 | [6 empty] | DONE
100 | 563 | McAllen | 1 | TX | 156275 10/28/03 | 2003-11-07 |  |  |  | 700 | 303 |  |  |  | water softner on site | water softner on site | YES | NO
100 | 594 | Laredo | 1 | TX | 156264 10/27/03 | 2004-03-16 |  |  |  | 440 | 265 |  |  |  |  | YES | NO | NO
100 | 602 | San Antonio | 1 | TX | 156305 10/28/03 | 2003-11-17 |  |  |  | 310 | 305 |  |  |  |  | YES | NO | NO
| 617 | Lake Jackson |  | TX | 156262 10/27/03 | 2003-11-07 |  |  |  | 550 | 145 |  |  |  | water softner on site | water softner on site | YES | NO
| 629 | Parkersburg |  | WV | 228235 10/3/05 | 2005-10-19 |  |  |  | 330 | 287 | [6 empty] | DONE
97-120 | 680 | San Antonio | 1 | TX | 156306 10/28/03 | 2003-11-13 |  |  |  | 300 | 276 |  |  |  |  | YES | NO | NO
| 694 | Tampa |  | FL | 229700 11/1/05 | 2005-11-16 |  |  |  | 300 | 180 |  |  | NEW |  |  |  | DONE
| 786 | Columbus |  | OH | 228265 10/3/05 | 2005-10-21 |  |  |  | 320 | 115 | [6 empty] | DONE
| 884 | Chesapeake |  | VA | 229437 10/19/05 | 2005-10-25 |  |  |  | 2808 | 33 |  |  | NEW |  |  |  | DONE
DTO | 898 | San Angelo | 1 | TX | 156298 10/27/03 | 2003-11-07 |  |  |  | 1500 | 466 |  |  |  | water softner on site | water softner on site | YES | NO
50 | 976 | Midland | 1 | TX | 156281 10/28/03 | 2003-11-07 |  |  |  | 1700 | 431 |  |  |  | water softner on site | water softner on site | YES | NO
| 978 | Tampa |  | FL | 229696 10/26/05 | 2005-11-03 |  |  |  | 320 | 215 |  |  | NEW |  |  |  | DONE
| 1014 | Amarillo |  | TX | 144214 8/26/03 | 2003-09-23 |  |  |  | 1000 | 226 |  |  |  | water softner on site | water softner on site | YES | NO
| 1029 | Conroe |  | TX | 156152 10/27/03 | 2003-11-07 |  |  |  | 340 | 146 |  |  |  | water softner on site | water softner on site | YES | NO
| 1036 | Lubbock |  | TX | 156270 10/27/03 | 2003-11-05 |  |  |  | 1200 | 21 |  |  |  |  | NO | NO | NO
| 1043 | San Antonio |  | TX | 168217 3/23/04 | 2004-04-14 |  |  |  | 260 | 295 |  |  |  | Water test kit sent out 3 times b-4 finally rec'd back ! | YES | NO | NO
| 1069 | El Paso |  | TX | 156167 10/27/03 | 2003-11-05 |  |  |  | 390 | 122 |  |  |  | water softner on site, but not working | water softner on site, but not working | YES BUT NOT WORKING | NO
| 1070 | Spring |  | TX | 156343 10/24/03 | 2003-12-18 |  |  |  | 350 | 55 |  |  |  |  | NO | NO | NO
| 1071 | The Woodlands |  | TX | 156344 10/28/03 | 2003-11-25 | 131312 M16254 | 2041 7/21/03 | 2003-08-01 | 340 | 47 | 2 - P | UP |  |  | NO | NO | NO
| 1092 | Sherman |  | TX | 180427 6/25/04 | 2004-07-13 | 180426 M38715 | install handled on site | 2004-07-16 | 400 | 112 | 2 - P | UP |  |  | NO | NO | NO
| 1109 | Lufkin |  | TX | 156272 10/27/03 | 2003-11-05 |  |  |  | 350 | 23 |  |  |  | water softner on site | water softner on site | YES | NO
| 1215 | Spring |  | TX | 156334 10/28/03 | 2003-11-07 |  |  |  | 330 | 45 |  |  |  | water softner on site | water softner on site | YES | NO
| 1244 | Tomball |  | TX | 182644 8/23/04 | 2004-09-17 | 182645 M43763 | install handled on site | 10/13/04 | 370 | 65 | 2 - P | UP |  |  | NO | NO | NO
| 1265 | San Antonio |  | TX | 156308 10/27/03 | 2003-11-07 |  |  |  | 350 | 279 |  |  |  |  | YES | NO | NO
| 1279 | Tampa |  | FL | 229685 10/26/05 | 2005-11-14 |  |  |  | 300 | 170 |  |  | NEW |  |  |  | DONE
| 1399 | Tampa |  | FL | 229683 10/26/05 | 2005-11-14 |  |  |  | 300 | 200 |  |  | NEW |  |  |  | DONE
| 1450 | McAllen |  | TX | 156276 10/24/03 | 2003-11-17 |  |  |  | 257 | 257 |  |  |  |  | YES | NO | NO
| 1477 | Homestead |  | PA | 228248 10/3/05 | 2005-10-19 |  |  |  | 300 | 175 | [6 empty] | DONE
| 1490 | Goodyear |  | AZ | 131319 7/1/03 | 2003-09-10 | 131320 M16353 | install handled on site | 7/1/03 | 410 | 108 | 2 - P | NO |  |  | NO | NO | NO
| 1507 | Oceanside |  | CA | 181598 7/26/04 198351 9/17/04 | 2004-10-05 | 181599 M41425 | install handled on site | 10/19/04 | 430 | 224 | 2 - P | UP |  | 9/17-rec'd empy box for H20 sample | NO | NO | NO
| 1514 | Chula Vista |  | CA | 168707 4/5/04 | 2004-04-22 | 168710/170026 M33451/M35784 | install handled on site | 6/18/04 | 400 | 231 | 2 - P | UP |  |  | NO | NO | NO
| 1553 | Scottsdale |  | AZ | 206935 2/11/05 | 2005-02-28 | 206936 M58019 | install handled on site | 2005-03-31 | 370 | 231 | BYPASS UNITS PKG C | YES |  | shipped 1st repl tank on 5/18/05, shipped 2nd repl Uptaste tank on 6/17/05 | NO | NO | NO
| 1564 | Corona |  | CA | 181876 8/3/04 | 2004-10-01 | 181877 M42003 | install handled on site | 2004-10-15 | 340 | 178 | 2 - P | UP |  |  | NO | NO | NO
| 1567 | Corona |  | CA | 157389 11/11/03 | 2004-01-13 | 157386 M25309 | install handled on site | 2/19/04 | 410 | 243 | 2 - P | UP |  |  | NO | NO | NO
S04-162R | 1638 | Odessa | 1 | TX | 166047 2/4/04 | 2004-05-19 | 165678 &175696 M29560 | install handled on site | 3/15/04 | 1300 | 470 | 2 - P | UP |  | water softener ??? | water softener ??? | water softener ??? | NO
| 1639 | Elizabethtown |  | KY | 228281 9/30/05 | 2005-10-14 |  |  |  | 330 | 225 |  |  | NEW |  |  |  | DONE
S04-162R | 1664 | Peoria | 1 | AZ | 181955 8/4/04 | 2004-08-30 | 181956 M42140 | install handled on site | 2004-10-14 | 700 | 260 | 2 - P | UP |  |  | YES | NO | NO
| 1709 | Tampa |  | FL | 229698 10/26/05 | 2005-11-08 |  |  |  | 350 | 215 |  |  | NEW |  |  |  | DONE
| 1734 | Canton |  | OH | 183154 9/2/04 | 2004-10-27 | 183155 M44634 | install handled on site | 2004-11-18 | 400 | 161 | 2 - P | UP |  |  | NO | NO | DONE
| 1734 | Canton |  | OH | 228256 9/30/5 | 2005-10-12 |  |  |  | 500 | 168 |  |  | NEW |  |  |  | DONE
| 1755 | Jacksonville |  | NC | 182265 8/12/04 | 2004-09-17 | 182266 M42603 | install handled on site | 2004-10-19 | 360 | 27 | 2 - P | UP |  |  | NO | NO | NO
| 1776 | San Antonio |  | TX | 207387 2/22/05 | 2005-03-09 | 207389 M58033 | install handled on site | 2005-03-24 | 260 | 292 | BYPASS UNITS PKG C | YES |  | shipped repl Uptaste tank on 5/18/05 | YES | NO | NO
| 1777 | San Antonio |  | TX | 228307 9/30/05 | 2005-10-25 |  |  |  | 280 | 299 |  |  | NEW |  |  |  | DONE
| 1778 | San Antonio |  | TX | 228305 9/30/05 | 2005-10-28 |  |  |  | 330 | 280 |  |  | NEW |  |  |  | DONE
| Store # | City |  | ST | Water test kit PO# & date sent out | date rec'd water test kits back | Ord#&Chick-fil-A PO# | PO# & date to installer | Ship Date | TDS | Hardness | Current Equipment | Up Taste | Status | Comments | Water Softener Needed | Existing Water Softener | NEW Water Test Needed | Recommendations
HIGH TDS UNITS